# Backlog, Sprint Plan & Team Responsibilities

ComicCraft — AI Comic Story Creator

| Team ID | SWTID-2026-4633 |
| --- | --- |
| Team Size | 4 |
| Team Leader | Priyadharshini K |
| Team Members | Prasannadevi R; Prateeksha S S; Ranjanipriya M |

Basis: supplied ComicCraft source archive and README. Statements about current behavior reflect the files reviewed; proposed work is labeled as recommendations. No live deployment or third-party provider configuration was inspected.

# 1. Planning assumptions

A four-person team will deliver a working prototype in incremental milestones. Sprint length, calendar dates, individual availability, and estimates were not supplied; the sequence below is a proposed plan and should be adapted by the team. The code archive indicates a prototype with core generation, preview, PDF export, and three basic tests, but tests were not runnable in this document-preparation environment because pytest is not installed.

Suggested responsibility assignments below are planning proposals based on project modules, not confirmed skill assignments. The Team Leader remains Priyadharshini K; the team should confirm individual preferences and capacity.

# 2. Proposed backlog

| ID | Work item | Priority | Acceptance / evidence |
| --- | --- | --- | --- |
| CC-01 | Local setup, dependency install, configuration and secret handling | Must | Fresh environment can start; no real credentials committed; setup steps tested. |
| CC-02 | Prompt form, field validation and responsive UI | Must | Required prompt and controls validate; errors retain inputs and are understandable. |
| CC-03 | Five-panel outline and story generation | Must | Valid structured output contains five ordered panels; malformed output fails safely. |
| CC-04 | Panel image generation and provider selection | Must | Five image artifacts map to correct panels; provider failures are surfaced. |
| CC-05 | Comic preview and PDF export | Must | Preview and PDF contain the same five panels, readable text, and matching illustrations. |
| CC-06 | API contract and health/image test routes | Must | Documented schemas, validation responses, health check and image-test path work. |
| CC-07 | Automated tests and UAT record | Must | Tests cover core routes, validation, mocked generation, export and failure paths; results recorded. |
| CC-08 | Privacy, safety, abuse and operational readiness | Must before shared release | Provider disclosure, content guidance, input limits, rate/access controls, logging/retention decisions reviewed. |
| CC-09 | Panel editing, persistence, accounts or collaboration | Could / defer | Separate product decision; not evidenced in supplied code. |

# 3. Proposed milestone plan (no calendar dates assumed)

| Sprint / milestone | Focus | Definition of done |
| --- | --- | --- |
| Sprint 1 — Foundation | Repository setup, configuration, app startup, form and schema validation. | Fresh setup documented; home and health routes work; field boundaries tested; secrets excluded. |
| Sprint 2 — AI pipeline | Gemini outline/story integration and image provider integration. | Mocked provider tests pass; exactly five validated panels; errors/timeouts are controlled; provider disclosure drafted. |
| Sprint 3 — Preview and export | Panel pairing, browser preview, PDF generation, UX polish. | Five images/story entries map in order; PDF fidelity/readability reviewed; failed export behavior documented. |
| Sprint 4 — Quality and handover | Regression tests, UAT, security/privacy review, documentation, release decision. | Executed test report and known issues; UAT feedback logged; production blockers and rollback/runbook documented. |

# 4. Suggested team responsibilities (confirm with team)

| Member | Suggested focus | Typical deliverables |
| --- | --- | --- |
| Priyadharshini K (Team Leader) | Coordination, scope decisions, integration and final review | Backlog/status, cross-module decisions, acceptance/sign-off, final demo. |
| Prasannadevi R | UI/UX, templates, accessibility and user documentation | Home/preview templates, responsive/accessibility checklist, user guide. |
| Prateeksha S S | AI pipeline, prompt design and creative-output evaluation | Gemini outline/story workflow, image prompts/provider evaluation, sample evaluation set. |
| Ranjanipriya M | API, schemas, exports, testing and deployment checklist | FastAPI routes/validation, PDF/export checks, test record, deployment/security checklist. |

This allocation is a practical starting point only. Members may pair-review each other’s work; all four should review acceptance criteria, safety/rights guidance, and final UAT.

# 5. Risk register

| Risk | Impact | Mitigation / owner action |
| --- | --- | --- |
| Gemini/image provider outage, quota, or model changes | High | Pin/test model configuration, use timeouts and bounded retries, provide clear errors and a provider smoke test. |
| Generated story or images are inconsistent or unsuitable | Medium–High | Define content guidelines; test representative/adversarial prompts; require user review and provide regeneration/editing in future scope. |
| Prompts or generated assets disclosed/retained by providers or logs | High | Map data flow, review current provider terms, disclose external processing, minimize data, redact logs, decide deletion/retention. |
| PDF/font/image export defect or filesystem exhaustion | Medium | Test Unicode and long text, cap output, handle failures, monitor and expire generated files. |
| Concurrent requests overwrite files or reveal another user’s files | High if shared | Unique random per-job identifiers, authorization/ownership, isolated storage and retention controls before multi-user release. |
| Test suite not run or evidence mistaken as passed | Medium | Record execution environment/results explicitly; automate CI and block release on defined failures. |

# 6. Team working agreements and reporting

Use issues/commits to link backlog items to code and tests; review API/schema changes with dependent contributors.

No secrets in source control, screenshots, issue logs, or project documents; use dummy credentials in examples.

A sprint item is done only when acceptance evidence and known limitations are recorded.

Do not describe a local prototype as public-ready until security, privacy, moderation, reliability, and UAT gates are complete.